## Product BackLog
Project | Key | Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Resolved | Affects Version/s | Fix Version/s | Component/s | Due Date | Original Estimate | Remaining Estimate | Time Spent | Environment | Description | Progress | Estimate- Man Hours | Due Date | Business Requester | QA Contact | QA Comments | Sponsor | Primary system | Project Status | Project Lead | Technology Sponsor | Tech Lead | Business Line | QA Lead | BA Lead | Story Points | Project long description | Business benefit | Designer Assigned | Delivery Ownership | Business Area | Business Region | Sponsor Approved | QA Comments | QA Required | Release Date | L0 Man-Day Estimate | Last Comment | Release # | Sprint | Fixed versions | Planned End Date | Planned Start Date
CitiRisk Commercial | C1590171-6608 | C1590171-6479 Approving Facility in Temp Ext CA | Sub-task | Closed | Critical | Resolved | Gu,BaoWan | Nilanjan Chakraborty | Nilanjan Chakraborty | 2014-04-07 16:25 | 2014-07-23 12:36 | 2014-07-23 12:36 | CitiRisk Prod V1.2 | CitiRisk Prod V1.2 | Facility Template_DO_NOT_USE | 2014-04-11 |  |  |  | DEV, INT1-1 | As per the discussion with release management team, this item will be scoped V1.2 onwards. 1. Please list the files change 2. Please list the test cases 3. Please update the test result in INT-1 Let's keep the fix ready in trunk and testing done in Int-1. | [27 empty] | This task is complete |  |  | CitiRisk ProdV1.2
CitiRisk Commercial | C1590171-6367 | Code Generation : Generated latest beans from code generator tool | New Requirement | Closed | Major | Fixed | Kherde,Milind | Kherde,Milind | Kherde,Milind | 2014-03-25 04:48 | 2014-08-15 14:24 | 2014-04-29 06:31 |  | CitiRisk Prod V1.2 |  |  |  | 0 | 86400 |  | Generated latest beans from code generator tool by configuring to : 1) BusinessService Branch : https://svn.nam.nsroot.net:9050/svn/159017/aris/CitiRisk/BusinessServices/branches/BusinessServices_CRAFT_Removal/” 2) UAT Database | 100% | [26 empty] | Re-generated the latest bean controller using above configuration. After mannually fixing the compilation error, changes has been checked-in at https://svn.nam.nsroot.net:9050/svn/159017/aris/CitiRisk/Common/branches/CitiRiskFlexUINonCraft/src/com/citi/no
CitiRisk Commercial | C1590171-6381 | Issues in generated beans | New Requirement | Development in Progress | Major | Unresolved | Unassigned | Kherde,Milind | Kherde,Milind | 2014-03-26 02:10 | 2015-01-28 11:48 |  |  | CitiRisk Prod V1.2 | [6 empty] | This is parent jira to track all the issues encountered in generated bean files. Please like all your issues fixes to this master ticket for tracking. | [29 empty] | Sprint 1
CitiRisk Commercial | C1590171-6703 | C1590171-6627 Temp Ext Scenario | Sub-task | Closed | Major | Resolved | Balaji Ravindran Chennakesava | Nilanjan Chakraborty | Nilanjan Chakraborty | 2014-04-14 14:05 | 2014-07-23 12:41 | 2014-07-23 12:41 | CitiRisk Prod V1.1 | CitiRisk Prod V1.2 | Facility Admin_DO_NOT_USE | 2014-04-25 |  |  |  | INT-1 | Even without this change today Rapid CA is gtting approved in Temp Ext. Need investigation, why the approved Facility remains 'N/A Overdue Review' unless the CitiRisk CA is availed. As per the understandling the existing version should get available once customer review ext date is transferred and the Rapid CA is approved. | [27 empty] | This is completed |  |  | CitiRisk ProdV1.1
CitiRisk Commercial | C1590171-7060 | C1590171-6171 Facility Service Modification for CA short Form | Sub-task | Closed | Major | Resolved | Gu,BaoWan | Subhankar Jana | Subhankar Jana | 2014-06-02 14:42 | 2014-07-23 12:46 | 2014-07-23 12:46 | CitiRisk Prod V1.2 | CitiRisk Prod V1.1, CitiRisk Prod V1.2 | Facility Admin_DO_NOT_USE | [5 empty] | Facility Services modification for CA short form changes | [27 empty] | Completed
CitiRisk Commercial | C1590171-11409 | Need clarification FI PSE Validation. | Inquiry | Closed | Major | Resolved | Subhash Chand | Subhash Chand | GIRISH BYAKOD | 2015-03-26 17:05 | 2015-04-09 17:25 | 2015-04-09 17:25 |  | CitiRisk Prod V1.2 | Credit Analysis V2_DO_NOT_USE, V2 Requirements Inquiry | 2015-04-10 |  |  |  |  | FI and PSE Validation Information in FRD is not enough. The new clarification from BA team does not seems right (that all Facilities in should have obligor with same exact segment code) | [27 empty] | Got the FI PSE Mappings. Based on that implementation will be done...
CitiRisk Commercial | C1590171-14376 | PRB0000052458 - Blackberry / Email Approval issue - Return to Analysis | Defect - PROD | Closed | Major | Resolved | Pareek,Sonal | More,Shivanjali | More,Shivanjali | 2015-06-30 14:43 | 2015-08-20 02:27 | 2015-08-20 02:27 |  | CitiRisk Prod V1.2 | Approval_DO_NOT_USE | [5 empty] | In Email Approval -When Approver clicked on Return to Analysis link - Approval don't change any contents of mail and submit email/CA. The CA is not sent back to Analysis . No changes to workflow is happening . | [27 empty] | Code fixed and tested by QA team , moved to production.
CitiRisk Commercial | C1590171-6589 | C1590171-6323 Dashboard - Junit Testing | Sub-task | Closed | Minor | Fixed | Kataria,Sumeet | Kherde,Milind | Kherde,Milind | 2014-04-07 07:25 | 2014-05-06 06:42 | 2014-04-21 17:43 | CitiRisk Prod V1.2 | CitiRisk Prod V1.2 | Dashboard_DO_NOT_USE | [5 empty] | Start Writing Junit test cases for generated code only, with business services being mocked up Medium Size SDRs: ASSIGN_PROXY_BASE_USERS CHECK_USER_FOR_NEXT_LEVEL CHECK_USER_FOR_NEXT_LEVEL_INITIATION CRC_GET_ALL_CURRENCY_RATE CRC_UPDATE_DELETE_DATA ENTITLEMENT_USING_CUSTOMERM_ATTRIBUTE GET_PROXY_USERS GET_USER_WITH_PERMISION_CODE POPULATE_APPROVER_USER_FROM_GES PREPARE_ENTITLEMENT_USING_CUSTOMER_ATTRIBUTE GET_WIGDGET_XML Very Big Size SDRs: ADD_ATTRIBUTE_TO_APPROVAL_ANALYSIS_MODULE GENERATE_BATCH_ALERTS GENERATE_BATCH_ALERTS_FOR_EW GENERATE_USER_ALERTS GENRATE_DRM_REPORT DASHBOARD_INIT_DATA_TEST | [27 empty] | All Jnuits are completed. One issue found in crcExtImpl.java. Issue is fixed and checked-in with proper comment. |  | Sprint 1
CitiRisk Commercial | C1590171-6247 | Develop and test Front Controller PoC | New Requirement | In QA | Trivial | Unresolved | Pagare,Prakash | Ranawat,Dhirendra | Ranawat,Dhirendra | 2014-03-19 06:51 | 2014-04-29 07:07 |  |  | CitiRisk Prod V1.2 | [6 empty] | Develop and test front controller PoC | [27 empty] | Done. |  | Sprint 1
CitiRisk Commercial | C1590171-6248 | Connect Auto Generated Beans and Generated Controllers to the Front Controller | New Requirement | In QA | Trivial | Unresolved | Pagare,Prakash | Ranawat,Dhirendra | Ranawat,Dhirendra | 2014-03-19 06:54 | 2014-04-29 07:08 |  |  | CitiRisk Prod V1.2 | [6 empty] | Front controller would need a mapping between varous actionNames and generated controllers. Create mapping for all the module as part of this task. | [27 empty] | Done. |  | Sprint 1
CitiRisk Commercial | C1590171-6249 | Analysis - Review Completeness of Auto Generated Beans from Code Generator Tool | New Requirement | In QA | Trivial | Unresolved | Ranawat,Dhirendra | Ranawat,Dhirendra | Ranawat,Dhirendra | 2014-03-19 06:56 | 2014-03-20 10:26 |  | CitiRisk Prod V1.2 | CitiRisk Prod V1.2 | Analysis_DO_NOT_USE | [5 empty] | Compare SDRs used in module during V1 and ensure that all the used ones and available in generated code. | [27 empty] | Checked the SDRs present in the Generated code. "GET_ORR_BASED_ON_GROUP" is missing. |  | Sprint 1
CitiRisk Commercial | C1590171-6250 | Approval - Connect Auto Generated Beans and Generated Controllers to the Front Controller | New Requirement | Closed | Trivial | Fixed | Rastogi,Gaurav | Singh,Shivendra | Singh,Shivendra | 2014-03-19 07:00 | 2014-08-15 14:24 | 2014-03-31 02:53 |  | CitiRisk Prod V1.2 | Approval_DO_NOT_USE | [5 empty] | Front controller would need a mapping between varous actionNames and generated controllers. Test the mapping for the credit apporval module. Whether all the SDR's are mapped to the front controller.
CitiRisk Commercial | C1590171-6251 | Analysis - Identify Dead Code for removal | New Requirement | In QA | Trivial | Unresolved | Ranawat,Dhirendra | Ranawat,Dhirendra | Ranawat,Dhirendra | 2014-03-19 07:01 | 2014-08-04 07:47 |  |  | CitiRisk Prod V1.2 | Analysis_DO_NOT_USE | [5 empty] | Go through generated code and verify if all the generated methods are used. All the potentially unused methods should be tagged and removal towards the end of dev cycle. Only tagging is expected as part of this defect. | [29 empty] | Sprint 1
CitiRisk Commercial | C1590171-6252 | Analysis - Bean Optimization and Refactoring | New Requirement | Closed | Trivial | Resolved | Mehrotra,Sonali | Ranawat,Dhirendra | Ranawat,Dhirendra | 2014-03-19 07:03 | 2014-08-15 14:24 | 2014-08-04 08:48 |  | CitiRisk Prod V1.2 | Analysis_DO_NOT_USE | [5 empty] | Reuse and Remove duplicate code from generated code. | [27 empty] | Due to newly regenerated code, optimization changes need to be done again. Marking as QA failed because there is no way to revert the status
CitiRisk Commercial | C1590171-6253 | Dashboard- Review Completeness of Auto Generated Beans from Code Generator Tool | New Requirement | Closed | Trivial | Fixed | Kherde,Milind | Raval,Chinmay | Raval,Chinmay | 2014-03-19 07:08 | 2014-08-15 14:24 | 2014-04-30 01:26 |  | CitiRisk Prod V1.2 | Dashboard_DO_NOT_USE | [5 empty] | Compare SDRs used in module during V1 and ensure that all the used ones and available in generated code.
CitiRisk Commercial | C1590171-6254 | Origination - Review Completeness of Auto Generated Beans from Code Generator Tool | New Requirement | Closed | Trivial | Resolved | Pravin Vijay Singh | Pravin Vijay Singh | Pravin Vijay Singh | 2014-03-19 07:09 | 2014-10-08 05:14 | 2014-10-08 05:14 |  | CitiRisk Prod V1.2 | Origination_DO_NOT_USE | [5 empty] | Compare SDRs used in module during V1 and ensure that all the used ones and available in generated code. | [29 empty] | Sprint 1
CitiRisk Commercial | C1590171-6255 | Dashboard - Identify Dead Code for removal | New Requirement | Closed | Trivial | Fixed | Raval,Chinmay | Raval,Chinmay | Raval,Chinmay | 2014-03-19 07:10 | 2014-08-15 14:24 | 2014-04-29 06:46 |  | CitiRisk Prod V1.2 | Dashboard_DO_NOT_USE | [5 empty] | Go through generated code and verify if all the generated methods are used. All the potentially unused methods should be tagged and removal towards the end of dev cycle. Only tagging is expected as part of this defect. | [27 empty] | above mentioned methods are marked with annotation @LogSDRName and checked in.
CitiRisk Commercial | C1590171-6256 | Approval - Review Completeness of Auto Generated Beans from Code Generator Tool | New Requirement | Closed | Trivial | Fixed | Rastogi,Gaurav | Singh,Shivendra | Singh,Shivendra | 2014-03-19 07:16 | 2014-08-15 14:24 | 2014-05-05 02:48 |  | CitiRisk Prod V1.2 | Approval_DO_NOT_USE | [5 empty] | Compare SDRs used in module during V1 and ensure that all the used ones and available in generated code.

## Exercise
Project | Key | Story Summary | Issue Type | Status | Priority | Resolution | Assignee | Reporter | Creator | Created | Updated | Resolved | Component/s Module or Epic | Due Date | Original Estimate | Remaining Estimate | Time Spent | Environment | Description / Details / Acceptance Criteria | Progress | Estimate- Man Hours | Due Date | Business Requester | QA Contact | QA Comments | Sponsor | Primary system | Project Status | Project Lead | Technology Sponsor | Tech Lead | Business Line | QA Lead | BA Lead | Story Points | Project long description | Business benefit | Designer Assigned | Delivery Ownership | Business Area | Business Region | Sponsor Approved | QA Comments | QA Required | Release Date | L0 Man-Day Estimate | Last Comment | Release # | Sprint | Fixed versions | Planned End Date | Planned Start Date
DCU bank online website | DCUOB1.0 | As a user of DCU bank,I would like to have the ability to view my e-statement online,so that I may not have to go to my branch during branch hours. | New Req | Open | M | In Dev | Mr.Kumar | Cust Rep | Kavita Bhatia | 2/21/2017 | 2/22/2017 | Open | View e-statement | 2/28/2017 | 40 Man Hours | 32 Man Hours | 8 Man Hours | Dev | Acceptance criteria : Is there any time period e-statements will be available for viewing ? Yes 12 months. . Workflow -1.1 The user will enter the URL www.dcu.org 1.2 The system will display home page and will ask for login credentials.1.3 The user will enter his login credentials.1.4 The system will validate login credentials.1.5The system will provide viewing e statement tab on the main menu bar.1.6 On clicking on e-statement tab,system will display 'Account Summary option' .1.6 The user will select checking account option.1.7 The system will display statement available options.1.8 The user will select a particular period of the e-statement and then press view.1.9 The system will display selected period e- statement.1.10 The system will ask if the user wants to review/ print/ copy/ download selected e-statement .1.11 The user will select print option.1.12 The system will print the e-statement. | 20%complete | Original estimate | 2/28/2017 | Customer rep |  |  |  |  | Active | [6 empty] | 20 points | [13 empty] | Sprint 2
DCU bank online website | DCUOB2.0 | As a user of DCU bank,I would like to have the ability to change/ manage my account type online,so that I may not have to go to my branch during branch hours. | New Req | Open | Medium | In Dev | Mr.Mukka | Cust Rep | Kavita Bhatia | 2/21/2017 | 2/22/2017 | Open | changing account type | 2/28/2017 | 40 Man Hours | 32 Man Hours | 8 Man Hours | Dev | Workflow 2.1 - The user will enter the URL www.dcu.org 2.2 The system will display home page and will ask for login credentials.2.3 The user will enter his login credentials.2.4 The system will validate login credentials. 2.5 The user will click on accounts from left menu.2.6 The system will display all profile information and activities.2.7The user will select ' Manage/ change account type' in order to access the available types.2.8 Account's type management operations are displayed.2.9 The user will select the account he wish to change from the drop down.2.10 The system will ask him to choose the account type he wish to change to.2.11 The user will provide the inputs.2.12 The system will validate the availability of the account type and ask to verification code sent to registered phone number. 2.13 The user will input the verification code and select next to process the request.2.14 The system will verify the code, process the request and display the message ' Your request has been successfully submitted.You will receive a confirmation email soon.' | 20%complete | Original estimate | 2/28/2017 | Customer rep |  |  |  |  | Active | [6 empty] | 20 points | [13 empty] | Sprint 2
DCU bank online website | DCUOB3.0 | As a user of DCU bank,I would like to have the ability to pay my bills online,so that I may not have to go to my branch during branch hours. | New Req | Closed | High |  | Mr.Kumar | Cust Rep | Kavita Bhatia | 2017-12-01 | 2/22/2017 | Closed | Pay bills online | 1/26/2017 | 80 Man Hours | Zero | 88 Man Hours | User | Acceptance criteria 3.1- Can user pay bills to payees outside the U.S? No Acceptance criteria 3.2 - Can user use bill payment from outside the United States? Yes only if user is using a compatible browser. . Workflow 3.1 - The user will enter the URL www.dcu.org 3.2 The system will display home page and will ask for login credentials.3.3 The user will enter his login credentials.3.4 The system will validate login credentials. 3.5 The user will click on services and will select 'online bill payment'3.6 The system will ask to choose the bill category from a drop down like household,medical,mortgage,Insurance etc. to be paid 3.7 The user will select a category and then select a particular bill from that category to be paid.3.8 The system will ask to select a payee.3.9 The user will select a payee.3.10 The system will ask to schedule the payment( now, or on particular date) .3.11 The user will select a schedule now and system will ask to review theselected options of bill payment.3.12 The user will review and press continue3.13 The system will display the message of your request is processed with the confirmation code of the payment. | 100% complete | 88 Man Hours | 1/26/2017 | Customer rep |  |  |  |  | Closed | [6 empty] | 44 points | [13 empty] | Sprint 1
DCU bank online website | DCUOB4.0 | As a user of DCU bank,I would like to have the ability to add a payee/ bill to my e-bill payer,so that I may not have to go to my branch during branch hours. | New Req | Closed | High |  | Mr.Mukka | Cust Rep | Kavita Bhatia | 01/14/2017 12:00:00 AM | 2/22/2017 | Closed | Add a payee to e- bill payer | 1/22/2017 | 48 Man Hours | Zero | 44 Man Hours | User | Workflow 4.1 - The user will enter the URL www.dcu.org 4.2 The system will display home page and will ask for login credentials.4.3 The user will enter his login credentials.4.4 The system will validate login credentials. 4.5 The user will click on E-bill payer option.4.6 The system will display all the options related to e-bill payments.4.7 The user will select 'add a payee/bill '4.8 The system will ask what type of payee do you want to add and provide options like company, Individual,Bank,Credit Union etc.4.9 The user will select an option. 4.10 .The system will ask to add details of the payee.4.11 The user will put all the details of the payee. 4.12 The says ten will ask to review the details.4.13 After reviewing all the inputs , the user will click continue. 4.14 The system will validate the detailed input and display the message ' The payee is successfully added'. | 100% complete | 44 Man Hours | 1/20/2017 | Customer rep |  |  |  |  | Closed | [6 empty] | 22 points | [13 empty] | Sprint 1
DCU bank online website | DCUOB5.0 | As a user of DCU bank,I would like to have the ability to send money to third party user online,so that I may not have to go to my branch during branch hours. | New Req | Closed | High |  | Mr.Dutta | Cust Rep | Kavita Bhatia | 2017-12-01 | 2/22/2017 | Closed | Send money to third party | 1/26/2017 | 80 Man Hours | Zero | 88 Man Hours | User | Workflow 5.1 - The user will enter the URL www.dcu.org 5.2 The system will display home page and will ask for login credentials.5.3 The user will enter his login credentials.5.4 The system will validate login credentials. 5.5The user will select pay money option.5.6 The system will display the sub transaction interface.5.7 The user will choose' send money' to proceed.5.8 The system will display users' account summary 5.9 The user will click on continue.5.10 the system will ask for inputs of recipient validation information like name of recipient,e-mail,mobile,Rec code,amount,pay from(select an account),How to pay,send on - date,optional message etc.,5.11 The user will provide all the inputs and click continue 5.12 The system will validate all the imputed information.5.13 The user will click on send .5.14 The system will display the confirmation message' your request has been processed successfully ' and will generate a confirmation code for future references. | 100% complete | 88 Man Hours | 1/26/2017 | Customer rep |  |  |  |  | Closed | [6 empty] | 44 points | [13 empty] | Sprint 1